## Aishwarya
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | S.Aishwarya | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | S.Aishwarya | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | S.Aishwarya | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | Completed
4 | S.Aishwarya | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | Completed
5 | S.Aishwarya | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | Completed
6 | S.Aishwarya | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | S.Aishwarya | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | S.Aishwarya | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | S.Aishwarya | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | S.Aishwarya | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | S.Aishwarya | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | S.Aishwarya | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | S.Aishwarya | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | S.Aishwarya | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed

## Aneesha
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | A.Aneesha | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | A.Aneesha | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | A.Aneesha | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | Completed
4 | A.Aneesha | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | Completed
5 | A.Aneesha | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | Completed
6 | A.Aneesha | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | A.Aneesha | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | A.Aneesha | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | A.Aneesha | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | A.Aneesha | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | A.Aneesha | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | A.Aneesha | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | A.Aneesha | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | A.Aneesha | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed

## Mythili
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | G.Mythili | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | G.Mythili | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | G.Mythili | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | ABSENT
4 | G.Mythili | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | ABSENT
5 | G.Mythili | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | ABSENT
6 | G.Mythili | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | G.Mythili | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | G.Mythili | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | G.Mythili | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | G.Mythili | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | G.Mythili | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | G.Mythili | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | G.Mythili | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | G.Mythili | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed

## S.Jaya Chithra
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | S.Jaya Chithra | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | S.Jaya Chithra | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | S.Jaya Chithra | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | ABSENT
4 | S.Jaya Chithra | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | Completed
5 | S.Jaya Chithra | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | Completed
6 | S.Jaya Chithra | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | S.Jaya Chithra | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | S.Jaya Chithra | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | S.Jaya Chithra | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | S.Jaya Chithra | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | S.Jaya Chithra | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | S.Jaya Chithra | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | S.Jaya Chithra | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | S.Jaya Chithra | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed