## Aishwarya
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | S.Aishwarya | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | S.Aishwarya | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | S.Aishwarya | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | Completed
4 | S.Aishwarya | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | Completed
5 | S.Aishwarya | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | Completed
6 | S.Aishwarya | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | S.Aishwarya | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | S.Aishwarya | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | S.Aishwarya | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | S.Aishwarya | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | S.Aishwarya | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | S.Aishwarya | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | S.Aishwarya | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | S.Aishwarya | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed
15 | S.Aishwarya | 2018-01-03 | 10:30 to 5:00 | learned basics of modules | In progress
16 | S.Aishwarya | 2018-01-04 | 10:30 to 5:00 | learned basics of modules | Completed
17 | S.Aishwarya | 2018-01-05 | 10:30 to 5:00 | Creating first Module | In progress
18 | S.Aishwarya | 2018-01-08 | 10:30 to 4:00 | Creating first Module | In progress
19 | S.Aishwarya | 2018-01-09 | 10:30 to 5:00 | Creating first Module | In progress
20 | S.Aishwarya | 2018-01-10 | 10:30 to 5:00 | Creating first Module | In progress
21 | S.Aishwarya | 2018-01-11 | 10:30 to 5:00 | Creating first Module | Completed
22 | S.Aishwarya | 2018-01-17 | 10:30 to 5:00 | Preparation for first review | Completed
23 | S.Aishwarya | 2018-01-19 | 10:30 to 5:00 | Working on individual modules | In progress
24 | S.Aishwarya | 2018-01-22 | 10:30 to 5:00 | Working on individual modules | In progress
25 | S.Aishwarya | 2018-01-24 | 10:30 to 5:00 | Working on individual modules | In progress
26 | S.Aishwarya | 2018-01-25 | 10:30 to 5:00 | Working on individual modules | In progress
27 | S.Aishwarya | 2018-01-29 | 10:30 to 5:00 | Working on individual modules | In progress
28 | S.Aishwarya | 2018-01-30 | 10:30 to 5:00 | Working on individual modules | In progress
29 | S.Aishwarya | 2018-01-31 | 10:30 to 5:00 | Working on individual modules | In progress
30 | S.Aishwarya | 2018-02-05 | 10:30 to 5:00 | Working on individual modules | In progress
31 | S.Aishwarya | 2018-02-06 | 10:30 to 5:00 | Working on individual modules | In progress
32 | S.Aishwarya | 2018-02-07 | 10:30 to 5:00 | Working on individual modules | In progress
33 | S.Aishwarya | 2018-02-08 | 10:30 to 5:00 | Working on individual modules | In progress
34 | S.Aishwarya | 2018-02-12 | 10:30 to 5:00 | Working on individual modules | In progress
35 | S.Aishwarya | 2018-02-03 | 10:30 to 5:00 | Working on individual modules | In progress
36 | S.Aishwarya | 2018-02-14 | 10:30 to 5:00 | Working on individual modules | In progress
37 | S.Aishwarya | 2018-02-15 | 10:30 to 5:00 | Working on individual modules | In progress
38 | S.Aishwarya | 2018-02-20 | 10:30 to 5:00 | Working on individual modules | In progress
39 | S.Aishwarya | 2018-02-21 | 10:30 to 5:00 | Working on individual modules | In progress
40 | S.Aishwarya | 2018-02-22 | 10:30 to 5:00 | Working on individual modules | In progress
41 | S.Aishwarya | 2018-02-23 | 10:30 to 5:00 | Absent
42 | S.Aishwarya | 2018-02-26 | 10:30 to 4:00 | Working on individual modules | In progress
43 | S.Aishwarya | 2018-02-27 | 10:30 to 4:00 | Review
44 | S.Aishwarya | 2018-02-28 | 10:30 to 4:00 | Review
45 | S.Aishwarya | 2018-03-01 | 10:30 to 4:00 | Working on individual modules | In progress
46 | S.Aishwarya | 2018-03-02 | 10:30 to 4:00 | Sports Day
47 | S.Aishwarya | 2018-03-03 | 10:30 to 4:00 | Holiday
48 | S.Aishwarya | 2018-03-04 | 10:30 to 4:00 | Holiday
49 | S.Aishwarya | 2018-03-05 | 10:30 to 4:00 | Exam
50 | S.Aishwarya | 2018-03-06 | 10:30 to 4:00 | Exam
51 | S.Aishwarya | 2018-03-07 | 10:30 to 4:00 | Exam
52 | S.Aishwarya | 2018-03-08 | 10:30 to 4:00 | Working on individual modules | In progress

## Aneesha
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | A.Aneesha | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | A.Aneesha | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | A.Aneesha | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | Completed
4 | A.Aneesha | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | Completed
5 | A.Aneesha | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | Completed
6 | A.Aneesha | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | A.Aneesha | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | A.Aneesha | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | A.Aneesha | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | A.Aneesha | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | A.Aneesha | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | A.Aneesha | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | A.Aneesha | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | A.Aneesha | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed
15 | A.Aneesha | 2018-01-03 | 10:30 to 5:00 | learned basics of modules | In progress
16 | A.Aneesha | 2018-01-04 | 10:30 to 5:00 | learned basics of modules | Completed
17 | A.Aneesha | 2018-01-05 | 10:30 to 5:00 | Creating first Module | In progress
18 | A.Aneesha | 2018-01-08 | 10:30 to 4:00 | Creating first Module | In progress
19 | A.Aneesha | 2018-01-09 | 10:30 to 5:00 | Creating first Module | In progress
20 | A.Aneesha | 2018-01-10 | 10:30 to 5:00 | Creating first Module | In progress
21 | A.Aneesha | 2018-01-11 | 10:30 to 5:00 | Creating first Module | Completed
22 | A.Aneesha | 2018-01-17 | 10:30 to 5:00 | Preparation for first review | Completed
23 | A.Aneesha | 2018-01-19 | 10:30 to 5:00 | Working on individual modules | In progress
24 | A.Aneesha | 2018-01-22 | 10:30 to 5:00 | Working on individual modules | In progress
25 | A.Aneesha | 2018-01-24 | 10:30 to 5:00 | Working on individual modules | In progress
26 | A.Aneesha | 2018-01-25 | 10:30 to 5:00 | Working on individual modules | In progress
27 | A.Aneesha | 2018-01-29 | 10:30 to 5:00 | Working on individual modules | In progress
28 | A.Aneesha | 2018-01-30 | 10:30 to 5:00 | Working on individual modules | In progress
29 | A.Aneesha | 2018-01-31 | 10:30 to 5:00 | Working on individual modules | In progress
30 | A.Aneesha | 2018-02-05 | 10:30 to 5:00 | Working on individual modules | In progress
31 | A.Aneesha | 2018-02-06 | 10:30 to 5:00 | Working on individual modules | In progress
32 | A.Aneesha | 2018-02-07 | 10:30 to 5:00 | Working on individual modules | In progress
33 | A.Aneesha | 2018-02-08 | 10:30 to 5:00 | Working on individual modules | In progress
34 | A.Aneesha | 2018-02-12 | 10:30 to 5:00 | Working on individual modules | In progress
35 | A.Aneesha | 2018-02-03 | 10:30 to 5:00 | Working on individual modules | In progress
36 | A.Aneesha | 2018-02-14 | 10:30 to 5:00 | Working on individual modules | In progress
37 | A.Aneesha | 2018-02-15 | 10:30 to 5:00 | Working on individual modules | In progress
38 | A.Aneesha | 2018-02-20 | 10:30 to 5:00 | Working on individual modules | In progress
39 | A.Aneesha | 2018-02-21 | 10:30 to 5:00 | Working on individual modules | In progress
40 | A.Aneesha | 2018-02-22 | 10:30 to 5:00 | Working on individual modules | In progress
41 | A.Aneesha | 2018-02-23 | 10:30 to 5:00 | Working on individual modules | In progress
42 | A.Aneesha | 2018-02-26 | 10:30 to 4:00 | Working on individual modules | In progress
43 | A.Aneesha | 2018-02-27 | 10:30 to 4:00 | Review
44 | A.Aneesha | 2018-02-28 | 10:30 to 4:00 | Review
45 | A.Aneesha | 2018-03-01 | 10:30 to 4:00 | Working on individual modules | In progress
46 | A.Aneesha | 2018-03-02 | 10:30 to 4:00 | Sports Day
47 | A.Aneesha | 2018-03-03 | 10:30 to 4:00 | Holiday
48 | A.Aneesha | 2018-03-04 | 10:30 to 4:00 | Holiday
49 | A.Aneesha | 2018-03-05 | 10:30 to 4:00 | Exam
50 | A.Aneesha | 2018-03-06 | 10:30 to 4:00 | Exam
51 | A.Aneesha | 2018-03-07 | 10:30 to 4:00 | Exam
52 | A.Aneesha | 2018-03-08 | 10:30 to 4:00 | Working on individual modules | In progress

## Mythili
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | G.Mythili | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | G.Mythili | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | G.Mythili | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | ABSENT
4 | G.Mythili | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | ABSENT
5 | G.Mythili | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | ABSENT
6 | G.Mythili | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | G.Mythili | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | G.Mythili | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | G.Mythili | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | G.Mythili | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | G.Mythili | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | G.Mythili | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | G.Mythili | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | G.Mythili | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed
15 | G.Mythili | 2018-01-03 | 10:30 to 5:00 | learned basics of modules | In progress
16 | G.Mythili | 2018-01-04 | 10:30 to 5:00 | learned basics of modules | Completed
17 | G.Mythili | 2018-01-05 | 10:30 to 5:00 | Creating first Module | In progress
18 | G.Mythili | 2018-01-08 | 10:30 to 4:00 | Creating first Module | In progress
19 | G.Mythili | 2018-01-09 | 10:30 to 5:00 | Creating first Module | In progress
20 | G.Mythili | 2018-01-10 | 10:30 to 5:00 | Creating first Module | In progress
21 | G.Mythili | 2018-01-11 | 10:30 to 5:00 | Creating first Module | Completed
22 | G.Mythili | 2018-01-17 | 10:30 to 5:00 | Preparation for first review | Completed
23 | G.Mythili | 2018-01-19 | 10:30 to 5:00 | Working on individual modules | In progress
24 | G.Mythili | 2018-01-22 | 10:30 to 5:00 | Working on individual modules | In progress
25 | G.Mythili | 2018-01-24 | 10:30 to 5:00 | Working on individual modules | In progress
26 | G.Mythili | 2018-01-25 | 10:30 to 5:00 | Working on individual modules | In progress
27 | G.Mythili | 2018-01-29 | 10:30 to 5:00 | Working on individual modules | In progress
28 | G.Mythili | 2018-01-30 | 10:30 to 5:00 | Working on individual modules | In progress
29 | G.Mythili | 2018-01-31 | 10:30 to 5:00 | Working on individual modules | In progress
30 | G.Mythili | 2018-02-05 | 10:30 to 5:00 | Working on individual modules | In progress
31 | G.Mythili | 2018-02-06 | 10:30 to 5:00 | Working on individual modules | In progress
32 | G.Mythili | 2018-02-07 | 10:30 to 5:00 | Working on individual modules | In progress
33 | G.Mythili | 2018-02-08 | 10:30 to 5:00 | Working on individual modules | In progress
34 | G.Mythili | 2018-02-12 | 10:30 to 5:00 | Working on individual modules | In progress
35 | G.Mythili | 2018-02-03 | 10:30 to 5:00 | Working on individual modules | In progress
36 | G.Mythili | 2018-02-14 | 10:30 to 5:00 | Working on individual modules | In progress
37 | G.Mythili | 2018-02-15 | 10:30 to 5:00 | Working on individual modules | In progress
38 | G.Mythili | 2018-02-20 | 10:30 to 5:00 | Working on individual modules | In progress
39 | G.Mythili | 2018-02-21 | 10:30 to 5:00 | Working on individual modules | In progress
40 | G.Mythili | 2018-02-22 | 10:30 to 5:00 | Working on individual modules | In progress
41 | G.Mythili | 2018-02-23 | 10:30 to 5:00 | Working on individual modules | In progress
42 | G.Mythili | 2018-02-26 | 10:30 to 4:00 | Working on individual modules | In progress
43 | G.Mythili | 2018-02-27 | 10:30 to 4:00 | Review
44 | G.Mythili | 2018-02-28 | 10:30 to 4:00 | Review
45 | G.Mythili | 2018-03-01 | 10:30 to 4:00 | Working on individual modules | In progress
46 | G.Mythili | 2018-03-02 | 10:30 to 4:00 | Sports Day
47 | G.Mythili | 2018-03-03 | 10:30 to 4:00 | Holiday
48 | G.Mythili | 2018-03-04 | 10:30 to 4:00 | Holiday
49 | G.Mythili | 2018-03-05 | 10:30 to 4:00 | Exam
50 | G.Mythili | 2018-03-06 | 10:30 to 4:00 | Exam
51 | G.Mythili | 2018-03-07 | 10:30 to 4:00 | Exam
52 | G.Mythili | 2018-03-08 | 10:30 to 4:00 | Working on individual modules | In progress

## S.Jaya Chithra
CONSTRUCTION ERP IMPLEMENTATION
S.NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | S.Jaya Chithra | 2017-12-11 | 10:30 to 4:00 | Disscussed About the Domain | Completed
2 | S.Jaya Chithra | 2017-12-12 | 10:30 to 4:00 | Learned about ERP domain | Completed
3 | S.Jaya Chithra | 2017-12-13 | 10:30 to 4:00 | Prepared for zeroth review | ABSENT
4 | S.Jaya Chithra | 2017-12-14 | 10:30 to 4:00 | Attedend Zeroth review | Completed
5 | S.Jaya Chithra | 2017-12-15 | 10:30 to 4:00 | Installed OpenErp and Learned some basics | Completed
6 | S.Jaya Chithra | 2017-12-18 | 10:30 to 4:00 | Went to placement drive | Completed
7 | S.Jaya Chithra | 2017-12-19 | 10:30 to 4:00 | Learned some of the modules of ERP | Completed
8 | S.Jaya Chithra | 2017-12-20 | 10:30 to 4:00 | installed some of the modules in openerp | In progress
9 | S.Jaya Chithra | 2017-12-21 | 10:30 to 4:00 | installed some of the modules in openerp | completed
10 | S.Jaya Chithra | 2017-12-22 | 10:30 to 4:00 | Learned some basic programs in python | In progress
11 | S.Jaya Chithra | 2017-12-26 | 10:30 to 4:00 | Learned some basic programs in python | completed
12 | S.Jaya Chithra | 2017-12-27 | 10:30 to 4:00 | Installing Ubuntu | In progress
13 | S.Jaya Chithra | 2017-12-28 | 10:30 to 4:00 | Installing Ubuntu | In progress
14 | S.Jaya Chithra | 2018-01-02 | 10:30 to 4:00 | Installing Ubuntu | Completed
15 | S.Jaya Chithra | 2018-01-03 | 10:30 to 5:00 | learned basics of modules | In progress
16 | S.Jaya Chithra | 2018-01-04 | 10:30 to 5:00 | learned basics of modules | Completed
17 | S.Jaya Chithra | 2018-01-05 | 10:30 to 5:00 | Creating first Module | In progress
18 | S.Jaya Chithra | 2018-01-08 | 10:30 to 4:00 | Creating first Module | In progress
19 | S.Jaya Chithra | 2018-01-09 | 10:30 to 5:00 | Creating first Module | In progress
20 | S.Jaya Chithra | 2018-01-10 | 10:30 to 5:00 | Creating first Module | In progress
21 | S.Jaya Chithra | 2018-01-11 | 10:30 to 5:00 | Creating first Module | Completed
22 | S.Jaya Chithra | 2018-01-17 | 10:30 to 5:00 | Preparation for first review | Completed
23 | S.Jaya Chithra | 2018-01-19 | 10:30 to 5:00 | Working on individual modules | In progress
24 | S.Jaya Chithra | 2018-01-22 | 10:30 to 5:00 | Working on individual modules | In progress
25 | S.Jaya Chithra | 2018-01-24 | 10:30 to 5:00 | Working on individual modules | In progress
26 | S.Jaya Chithra | 2018-01-25 | 10:30 to 5:00 | Working on individual modules | In progress
27 | S.Jaya Chithra | 2018-01-29 | 10:30 to 5:00 | Working on individual modules | In progress
28 | S.Jaya Chithra | 2018-01-30 | 10:30 to 5:00 | Working on individual modules | In progress
29 | S.Jaya Chithra | 2018-01-31 | 10:30 to 5:00 | Working on individual modules | In progress
30 | S.Jaya Chithra | 2018-02-05 | 10:30 to 5:00 | Working on individual modules | In progress
31 | S.Jaya Chithra | 2018-02-06 | 10:30 to 5:00 | Working on individual modules | In progress
32 | S.Jaya Chithra | 2018-02-07 | 10:30 to 5:00 | Working on individual modules | In progress
33 | S.Jaya Chithra | 2018-02-08 | 10:30 to 5:00 | Working on individual modules | In progress
34 | S.Jaya Chithra | 2018-02-12 | 10:30 to 5:00 | Working on individual modules | In progress
35 | S.Jaya Chithra | 2018-02-03 | 10:30 to 5:00 | Working on individual modules | In progress
36 | S.Jaya Chithra | 2018-02-14 | 10:30 to 5:00 | Working on individual modules | In progress
37 | S.Jaya Chithra | 2018-02-15 | 10:30 to 5:00 | Working on individual modules | In progress
38 | S.Jaya Chithra | 2018-02-20 | 10:30 to 5:00 | Working on individual modules | In progress
39 | S.Jaya Chithra | 2018-02-21 | 10:30 to 5:00 | Working on individual modules | In progress
40 | S.Jaya Chithra | 2018-02-22 | 10:30 to 5:00 | Working on individual modules | In progress
41 | S.Jaya Chithra | 2018-02-23 | 10:30 to 5:00 | Working on individual modules | In progress
42 | S.Jaya Chithra | 2018-02-26 | 10:30 to 4:00 | Working on individual modules | In progress
43 | S.Jaya Chithra | 2018-02-27 | 10:30 to 4:00 | Review
44 | S.Jaya Chithra | 2018-02-28 | 10:30 to 4:00 | Review
45 | S.Jaya Chithra | 2018-03-01 | 10:30 to 4:00 | Working on individual modules | In progress
46 | S.Jaya Chithra | 2018-03-02 | 10:30 to 4:00 | Sports Day
47 | S.Jaya Chithra | 2018-03-03 | 10:30 to 4:00 | Holiday
48 | S.Jaya Chithra | 2018-03-04 | 10:30 to 4:00 | Holiday
49 | S.Jaya Chithra | 2018-03-05 | 10:30 to 4:00 | Exam
50 | S.Jaya Chithra | 2018-03-06 | 10:30 to 4:00 | Exam
51 | S.Jaya Chithra | 2018-03-07 | 10:30 to 4:00 | Exam
52 | S.Jaya Chithra | 2018-03-08 | 10:30 to 4:00 | Working on individual modules | In progress